## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team and Freshman Seminar acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2171-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions, cross-team testing, and Freshman Seminar testing.
Team Name | 2201-swen-261-09-s2c-Beans
Testing Team Name | fill in when doing cross-team or Freshman Seminar testing

## Test Plan
User Story | Acceptance Criterion | Sprint 3 | Tester initials; date; comments (required if test failed)
As a Player I want to sign-in so that I can play a game of checkers. | Given that I have not yet signed in when I see the Home page then I must see a means to sign-in. (such as a link or button)
Given that I am not signed-in when I do click on the sign-in link then I expect to be taken to the Sign-in page, with a means to enter a player name.
Given that no one else is using my name when I enter my name containing at least one alphanumeric character and optionally spaces in the sign-in form and click the Sign-in button then I expect the system to reserve my name and navigate back to the Home page.
Given that I am on the Sign-in page when I enter a name that does not contain at least one alphanumeric character or contains one or more characters that are not alphanumeric or spaces and click the Sign-in button then I expect the system to reject this name and return the Sign-in page.
Given that someone else with my name has signed-in when I enter my name in the Sign-in form and click the Sign-in button then I expect the system to reject my sign-in and return the Sign-in page for me to try a different name.
Given that I am signed-in when I navigate to the Home page then I expect to see a list of all other signed-in players. (NOTE: in the next story you will use this list to pick opponents for checkers games.)
Given that I am not signed-in when I navigate to the Home page then I expect to see a message of how many players are signed-in but not a list of them (for privacy reasons).
As a Player I want to start a game so that I can play checkers with an opponent. | Given that I'm signed in when I view the Home page then I can start a game by selecting a player listed on the Home page.
Given that the player I selected isn't yet in a game when I select that player then the system will begin a checkers game and assign me as the starting (Red) player and my opponent as the White player.
Given that the player I selected is already in a game when I select that player then the system will return me to the Home page with an error message.
Given that I'm waiting for a game when another player selects a game with me then the system will automatically send me to the Game View as the White player. NOTE: the `home.ftl` HTML includes a `<meta>` tag that tells the browser to refresh the game every 5 seconds; thus you need to update the `GetHomeRoute` controller to handle the situation when a player is assigned a game.
Given a valid, initial game board when I drag a piece to a white space then the piece should not be droppable.
Given a valid, initial game board when I drag a piece to an occupied space then the piece should not be droppable.
Given a valid, initial game board when I drag a piece to an open space then the piece should be droppable. NOTE: In this Story the drop action should not do anything; piece movement will be the focus of future stories.
Given a valid, initial game board when I view the board in the browser then my pieces are oriented on the bottom of the board grid just like I would see the board if I were playing in the physical world.
As a Player I want to only be able to make legal moves on the Board so that the American rules of Checkers are satisfied. | Given that it its my turn when I put my piece on an invalid space then the game will tell me to try again.
Given I have just moved my piece when I go to backup my move then the game will put the checker in its original position (before the move).
Given that my piece is not kinged when I move my piece then I expect to only be able to move that piece toward my opponent.
As a player I want the turns to alternate so I can play against my opponent's moves. | Given I am playing against my opponent when I make a valid move then I expect my opponent to be able to go next.
Given I am playing against my opponent when I make a valid move and another capture is possible after my move then it become my turn so I can complete the multi-capture.
As a Player I want to be forced to capture an opponent Piece so that I can make progress towards winning. | Given that it is my turn when I move my piece over my opponent's piece then I will be forced to capture my opponent's piece.
As a Player I want to be forced to jump and capture multiple eligible opponent Pieces so that I can make quicker progress toward winning. | Given that it is my turn when I have the ability to jump multiple pieces then I must capture all jumpable opponent pieces.
As a Player I want to have the Game to end with me as a loser if I resign at any time so that I can begin another Game. | Given that I am in a game when I press the resignation button then I expect the game to end with me as the loser and my opponent as the winner.
Given that I am in a game when I choose to resign a game then I expect to be prompted to confirm my choice.
As a Player I want to have the Game to end with someone as the winner if all of a Player's Pieces are captured so that I can begin another Game. | Given that I am in a game when I capture all of my opponent's pieces then I expect the game to end with me as the winner and my opponent as the loser.
As a Player when a SINGLE Piece enters the king Row then I expect my Piece to become a KING so that it is able to move and capture backwards. | Given I am in a game when I am able to make a valid move into the Row furthest from me then the SINGLE Piece should become a KING.
As a Player I want to sign out of the web checkers application so I can leave the application and the lobby. | Given I leave the web checkers application when I log out then I will be brought to an inactive home view.
Given I want to leave the web checkers application when I log out then the total amount of players in the lobby are reduced by one.
Given I want to leave the web checkers application when I log out then I will be brought to an inactive home view.
Given I leave the web checkers application while in a game when I log out then my opponent will be awarded a victory.
As a Player I want to be able to play multiple games at once so that I can always be active against my opponents. | Given I want to have multiple games open when I open another game on the same account then I will be able to play both games at once.
Given I am in a game when I go back to the home page then I will be able to play another game with a different person.
As a Player I want to save past checker games so that I can review them at a later date. | Given I want to look at my past games when I press on the replay button for a game then I will be able to step through (forwards and backwards) the game's movements.
Given I want to step through my moves when I view a replay then when I finish viewing all moves, the forward button will be greyed out.
Given I want to step through my moves when I view a replay then when I start viewing my moves the step backwards button will be greyed out.
As a Player I want to be able to see the match statistics (score, piece count, etc.) so that I can visually see how the game is going. | Given I have just completed a game when I check my played games then I should see a set of statistics for each game.
Given I have just completed a game when I check my played games then I should see the Players involved as part of the statistics.
Given I have just completed a game when I check my played games then I should see the number of valid Moves as part of the statistics.
Given I have just completed a game when I check my played games then I should see the way that the game had ended (e.g. resignation or capture) as part of the statistics.
As a Player I do not want to win or lose if there is a tie so that the American rules for Checkers are satisfied. | Given I stall the game for too long when I reach 40 moves with out captures then I tie/draw the game.
Given I have no valid moves to make when it is my turn then I draw the game.
Given a draw occurs when a game is being played then the game ends.